## Sheet1
Risk | Probability | Impact | Mitigate | Monitoring | Assigned to(Management) | Impact on Project Success
Tech stack not compatible with each other | Medium | Delay the completion of each sprint and the propject as a whole | Research alternatives. E.g. GUI can be used instead of a web component | Ease of integration between compnent technoloogies. i.e. Is it easy to connect react to a java core | Deji | Catastrophic
Number of projected changes to the product requirements pre and post delivery | Medium | Disorganisation of team priorities and delay in project completion | Scale back on the scope of the project | Feasibility of use cases and difficulty in the implementation of features | Minh | Medium
Delivery of Incomplete or non functional product | High | Product may lack feature(s) or may not run at all | Stick to timeline, reassign easier tasks to less experienced team members and prioritize tasks effectively | Speed of task completion by team members | Deji | High
Build environment not working | Medium | Can't run our project demo | Make sure everything is working before class, have 2 laptops with working project | Check program versions, make sure they match up | Gahyun | Low
Team member can't showup to presentation | Low | Unable to explain their part of the presentation | Show up even if sick, in a car accident or dying | Contact members before start of class | Minh | Low
Git hub repo deleted | Low | Loss of project files | Local backups | Check git hub daily | Gahyun | Low
Rahim can't make it to class | Low | Class is cancelled | N/A | Check Blackboard and school email | Minh | Low

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only